Access and Service Delivery Committee

Report to

Minnesota Judicial Council

July 17, 2008

TABLE OF CONTENTS

Access and Service Delivery Committee Members	ii

Future Challenges for the Courts	1

Committee Background	2

Committee Charge	3

Process for Identifying Options	3

Considered Options	4

A Vision of the New Court System	4

Strategy: Increasing Staff Productivity—Staffing to the Most Efficient Norm	7

Strategy: Re-engineer Workflow in an Electronic Environment	8

Strategy:  Legislative and Court Policy Reform	10

Strategy:  Structure/governance issues	11

Recommended Options	11

Recommended Priorities	15

Summary of Recommended Actions	17

Appendices	18

Appendix A NCSC Consulting Services	20

Appendix B Partial List of Sources for Potential Options	24

Appendix C Other Potential Options	25

Appendix D Best Practices	29

Appendix E Option Cost Assessment by Priority	33

Appendix F Option Time Horizon by Priority	36

Appendix G Stakeholders Assessment By Priority	37

Appendix H Policy Authority by Priority	43

Appendix I (MNET)	45

Appendix J Options Short Description By Priority	46

# Access and Service Delivery Committee Members

Honorable John Rodenberg, Chair

Honorable David Knutson

Jerry Winter

Honorable Gregg Johnson

Honorable Lucy Wieland

Honorable Chuck Porter

Judy Besemer

Honorable Mike Kirk

Tim Ostby

Honorable Jerry Seibel

Honorable Jon Maturi

Honorable James Florey

Sue Dosal, Ex Officio

Project Staff

Heidi Green, Consultant

National Center for State Courts

Thomas Clarke, Vice President Research and Technology

Daniel Hall, Vice President Court Consulting Services

Report of the Access and Service Delivery Committee

to the

Minnesota Judicial Council

July 17, 2008

This report describes the charge to the Access and Service Delivery Committee (ASD Committee), the background leading to the Committee’s creation, the process the Committee used, the options it considered, the strategies that it identified, the options it recommends, and the priorities it recommends for implementing the options.  A number of appendices provide extensive details in all of these areas.

# Future Challenges for the Courts

Fundamental demographic shifts in the population present a long-term challenge for the courts that will extend well into the next decade.  The baby boom generation is just now beginning to hit retirement age.  Beginning in 2008 and extending into the next decade, Minnesota will see a 30 percent jump in workers reaching the average retirement age of 62.  Seniors over the age of 65 will exceed the number of school age children for the first time in our history.  The cost for government-funded social security, medical care, and public employee pensions for those aging baby boomers will put unprecedented financial pressures on local, state, and federal governments.  These pressures will shift government spending priorities to issues of aging and health and away from other state services, including the courts.

As people retire, they tend to earn less taxable income and begin relying on retirement benefits and accumulated savings.  As such and according to experts, they tend to pay less taxes and be more fiscally conservative than younger voters.  As the percent of retired people in the population grows, tax revenues needed to pay for state and local government decline.  Over the next decade, the baby boomers will change government spending priorities and their retirement will result in less tax revenue, putting the squeeze on all traditional state government spending—including the courts. Thus even in relatively strong economic times, the courts will face greater competition for tax dollars.

Moreover, as the baby boomers are retiring, the relative number of new workers in the state will be shrinking, creating competition for employees.   The state demographer estimates that the Minnesota workforce will continue to shrink over the next two decades and at a rate that exceeds the national average.

The courts face twin challenges in the future:

- Significant budget constraints no matter how meritorious the needs of the judicial branch or how essential the government function we fulfill.

- Smaller available workforce with significant competition for a limited pool of workers.

Minnesota will not be alone in requiring their government to examine ways in which it does business.  Other states are also struggling as our economy turns down and the baby boomers start retiring.  But like the private sector, those who are able to adapt to the changing times are most likely to succeed.

# Committee Background

The Judicial Council formed the Access and Services Delivery (ASD) Committee to begin the process of addressing a future of continuing revenue shortfalls and worker shortages. The Council’s charge to the Committee in February was to develop options for restructuring delivery systems, redesigning business processes, expanding the use of technology and prioritizing functions to provide appropriate levels of access and services statewide at the lowest cost given the projected fiscal and demographic outlook.

As part of the early strategic planning process, the Strategic Planning Committee was aware and mindful of financial constraints that would be facing the judiciary in the coming years.  As it developed, the onset of financial constraints was somewhat earlier and the severity greater, than originally anticipated.  This was due, in part, to the changing state budget forecasts during the time period from the fall of 2007 to the winter of 2007-2008.

In one of the early drafts of the proposed strategic plan, the Strategic Planning Committee was considering inclusion of a goal something like the following:

Explore ways to gain efficiencies in the way some court business processes are handled.  For example, process citations in central locations, process jury summons in central locations, use hearing officers in central locations through ITV.

Additionally, the Strategic Planning Committee was considering inclusion of a strategic goal something along the following lines:

Explore the appropriate level of service delivery necessary to provide access to justice throughout the state, including but not limited to, the number of court locations, services to be provided in each court location, the hours of operation, and the appropriate use of ITV.

As early as January 2008, it was evident that the judiciary was going to be experiencing financial constraints not previously anticipated—that the changing demographics and long-term fiscal decline predicted for the future had already started.  Given that the Strategic Planning Committee was already exploring the issues set forth above, the Council decided on January 18, 2008 “to examine the appropriate level of service delivery necessary to provide access to justice throughout the state,” and decided that the initiative should be undertaken immediately.

# Committee Charge

At its meeting on January 18, 2008, the Judicial Council authorized the formation of a committee to take a global look at the operations and structure of the judicial branch and develop recommendations for possible Council consideration and action. The Council provided that:

This examination would include, but not be limited to, the number of court locations, services to be provided in each court location, the hours of operation, the appropriate use of ITV, cost containment or reduction through technology and efficiencies to be gained in the way court business processes are handled through new methods (e.g. processing of citations and jury summons and use of hearing officers in central locations) and consideration of appropriate out-sourcing.

The Judicial Council requested the Chief Justice to appoint members to the newly created ASD Committee.  See Appendix A for a list of the Committee members.  Given the short time frame of the project, outside consultants from the National Center for State Courts (NCSC) were hired to assist the newly formed Committee.  (See Appendix B, p. 19 for the NCSC proposal.)  The Committee sought to create an evaluation environment that would encourage innovative thinking so that wide-ranging options could be gathered and considered regardless of how politically unpopular they might be.  The Committee reviewed options for restructuring delivery systems, redesigning business processes, expanding the use of technology, and prioritizing functions to provide the greatest levels of access and service statewide at the lowest cost.  The Committee was to report its initial findings to the Judicial Council at the July 2008 meeting.

# Process for Identifying Options

The Committee considered options from a wide variety of sources, both historical and current.  It solicited suggestions from a number of court groups and received several unsolicited communications from court staff and others.  No idea was considered off-limits initially, up to and including those that would require changes in the state constitution.  Attached as Appendix C, p. 24, is a partial list of the sources considered by the Committee.

The Committee initially decided to evaluate proposed options using four criteria:  cost impact, feasibility, service impact, and time impact.

- Cost impact is the net savings to the court system after deducting implementation and operational costs from cost savings.

- Feasibility is an assessment of possible constraints to implementation from all sources, including political resistance from key stakeholders.

- Service impact describes any improvements or reductions in service levels to court stakeholders.

- Time impact assesses how long it will take to implement the option and gain any benefits.

Early in the process the Committee thought about identifying potential out-sourcing opportunities and identified several criteria for use in determining likely candidates.  Ultimately, the Committee decided not to make any recommendations about out-sourcing.

The Committee considered ways to solicit input from various external court stakeholders on service impacts.  By definition, this is hard to do, since many court users are just not very knowledgeable about the court system in general and court services in particular.  It is especially difficult for users to imagine future business processes and services that do not currently exist.  One suggested approach was to hold facilitated focus groups with targeted groups of court stakeholders to gather input only on those options that appeared to strongly affect public services.  The Committee decided not to pursue this idea because of time and resource limitations.  Instead, the Committee members assessed the perceived feasibility of adopting the various options by stakeholder group.  Of course, these ratings reflect only the Committee’s guess at how those stakeholder groups would react.

# Considered Options

The Committee reviewed all submitted options from all sources.  A list of options considered, but not recommended, is provided in Appendix C, p.25.  Some options were screened out relatively quickly for the following reasons:

- Low impact on costs

- Long time to realize benefits

- Not feasible, especially politically

Past reports and suggestions from court personnel were so numerous that it was literally not possible to fully investigate all the suggestions.  The Committee attempted only to perform a reasonable screening of the options that would sift out the most promising candidates.  This sifting process turned out to be somewhat iterative, with some options being considered several times or in several forms as more information became available.

The Committee found a number of the suggested options to have significant merit as best practices, and should be encouraged by referral to the appropriate administrative committee for development, but are beyond the high-level perspective of the ASD Committee’s charge.  A list of the options identified as best practices, the options that the Committee studied, and the options that the Committee chose not to study are provided in Appendix E, p. 29.

# A Vision of the New Court System

Although the Committee decided ultimately to focus as a first phase of the ASD Committee work on changes that could be made over the next several years, it clearly saw that a more fundamental long-term redesign of the court system is necessary.  Recent initiatives already underway or completed in the Minnesota trial courts, such as state-funding and the new MNCIS technology, provide opportunities for increased efficiencies through centralization and greater public access to the courts through electronic service delivery.  To take full advantage of the opportunities presented by these innovations, the court will need to re-invent itself:  change the way it delivers services and provides access.  If successful, the court may actually find itself in the position of providing improved and better service in spite of the predicted labor shortage and funding downturn.

An analogy may be drawn from the banking industry.  The banking industry has experienced tremendous consolidation of companies in the last two decades, reducing costs through greater economies of scale, but at the same time adding electronic services so that today bank clients actually have greater access to their accounts and other banking services.  Several other states, most notably Utah, have already begun such a project to examine the opportunities provided by the new technologies and have found that the desired and required changes in court structure and case processing are quite significant. In the future, the courts will provide an increasing proportion of their services using the telephone and Internet rather than provide them solely by court employees at physical court locations.  Redesign of this sort may help improve service to the public while providing opportunities to save costs. Thus, in the longer term, the issue shifts away from current economic constraints toward desired service strategies.  Looked at from this perspective, the options and recommendations made by this Committee are really just first steps toward the court system of the future.

The Committee was able to identify four major initiatives or strategies that will help shape the court of the future.  The strategies are:

- Staff to the most efficient norm

- Re-engineer workflow in an electronic environment

- Legislative and court policy reform

- Structural and governance change (redistricting)

It is difficult to imagine the cumulative impact of the recommended strategies on the court system because some of the potential changes are quite dramatic.  A major reconfiguration of the court that includes structural, policy, and workflow change goes beyond the immediate scope of this report, but it is clear to the Committee that some appropriate body should systematically consider such ideas and deliberately begin planning for and adopting strategies to achieve the needed changes.  Using the example of the as yet unpublished Utah report on the redesign of their clerk duties, the Committee believes that a group other than this Committee should be convened to consider the long-term vision of service delivery in the Minnesota courts in a systematic way (see Recommended Action 3).

Examples of options that were considered by the Committee and then deferred to an analysis of the future court system by some other body include such ideas as:

- Redesign of the workflow in the court administrator’s office.

(e.g. Remaining work will need to be redesigned once significant changes in workflow occur from electronic filing, centralization, etc.)

- Redesign of the courtroom duties and processes.

(e.g. To take full advantage of the efficiencies derived from digital recording court room duties need to be examined and possibly re-deployed between staff groups, and is deferred for further study and comment as to details.)

- Redistricting and shifting of some functions out of the judicial branch (see Appendix D, p. 25.  Redistricting needs to be considered so that the court’s structure supports the future methods of court services delivery.)

More detailed descriptions of the four strategies identified by the Committee follows.

# Strategy: Increasing Staff Productivity—Staffing to the Most Efficient Norm

Staffing to the most efficient norm is more of an over-arching strategy than a single initiative.  In fact, it will consist of multiple initiatives over a number of years including centralization of services, increased electronic access to the court, remote case processing, and more.  Staffing to the most efficient norm implies that staff productivity will increase in all courts, regardless of court size, and that in the future technological and structural change will result in economies to even the smallest, most rural court locations.  Several of the most promising, relatively short-term, options that will support the strategy of staffing to the most efficient norm are recommended and prioritized in this report.  More significant changes in court business processes in support of the most efficient staffing norm will take longer to implement and should be investigated by a group appointed by the Judicial Council (see Recommended Action 3).

Achieving the most efficient staffing norm will take a mix of technical and business process innovations.  The options recommended below include both types of initiatives.  For example, the various “e-everything” options will provide a basis for allocating work in the most efficient way.  Just as important, business process improvements like the various payments options and the most promising recommendations from the NEAC report (see below in section on Considered Options) will help the courts operate more efficiently.

The Minnesota Court Staff Workload Assessment, 2004 clearly demonstrated the economies of scale that occur with size.  A subsequent analysis estimated that staffing to the most efficient norm could save up to $7,200,000 annually.  In general, larger courts are able to deploy staff more efficiently due to staff specialization.  The smallest courts, where a limited number of staff need to engage in a variety of tasks and specialization is not possible, demonstrated the least staff productivity.  This is not to say that staff in the smallest courts are not working hard, rather that the opportunity for economies to be gained by performing similar tasks repeatedly was not available.  These economies through specialization were also seen in the training required for implementing MNCIS.  Staff in the largest courts only needed to receive MNCIS training in the case type of their division.  For example, criminal division staff only needed to be trained on criminal, while family court staff only needed to be trained on family matters.  In contrast, staff from the smallest courts needed to be trained on all case types in MNCIS, as the daily variety inherent in their work included all case types.

The economies of scale that occur with specialization and repetitive tasks in the largest courts was recognized by the ASD Committee as it considered whether to recommend closing the state’s smallest courthouses.  The Committee found that savings from closing the smallest courts are relatively small while stakeholder opposition is expected to be high.  At this time the ASD Committee recommends maintaining local county court locations, although operating within the parameters of the most efficient staffing norms may require limited hours and services in some locations.  The ASD Committee found that some court administrators are already finding creative ways to achieve the staffing efficiencies of larger courts by managing resources more centrally.  An example of this is the regionalization of juror summons and questionnaire processing as currently conducted in the 9th Judicial District.  The 9th Judicial District recently coordinated the processing of all juror summons and juror eligibility questionnaires from its 17 counties under one centralized position.  The number of staff involved in juror processing dropped dramatically and the increase in staff productivity matched that of the state’s largest single-county districts.

The ASD Committee therefore endorsed in concept the strategy of assessing staff need and deploying court staff based on the most efficient staffing norms, regardless of court size.  In other words the options considered would be evaluated in part by the degree to which they increase staff productivity.

# Strategy: Re-engineer Workflow in an Electronic Environment

As much as the new technologies support the court’s vision for the future by providing the potential for greater access and better service to the public through electronic media and on-line communication, the economic reality of constrained resources, due to the demographic and political change previously described, must be considered when planning for the future and implementing the new technologies.  New technologies must support the court’s vision of service delivery, but ideally must also increase staff productivity in such a manner so as to achieve the access and service goals of the court in the future with increasingly limited resources.

The Minnesota courts are better placed than many other institutions to face the challenges of the future in large part because of the recent implementation of MNCIS, the new statewide case management system that employs the latest technologies.  The next phase of MNCIS implementation includes the integration of ancillary technologies, such as e-filing, that promise to increase worker productivity and allow the court to more efficiently communicate with its business partners.  These efficiencies will be especially important to the smallest courts, that will need to dramatically increase staff productivity.  However, in order to realize the greatest economies offered by the new technologies and maintain the highest level of service to the public possible, significant business process redesign is needed.  Old, traditional processes cannot be maintained with just a window dressing of new technology overlaid.

Both private industry and the executive branch of state government have moved beyond the idea that every service location must actually perform all the services offered by the enterprise.  This strategy offers an alternative, taking advantage of the new technologies, to offer access to all of the court’s services from every location or, in some cases, from non-court locations via the Internet, telephone, or other electronic means.  Centralizing or regionalizing the provision of these services, such as centralizing payables, and providing back-up in the form of remote case-processing capabilities, will free up local court staff to focus on those services that cannot be entirely automated, such as walk-in pro se help for domestic abuse petitioners.  The kind of economies that will come from re-engineering the court’s business process in a new electronic environment may allow the physical courthouses in local communities to be maintained with minimal staff, making their continued presence in the community a viable option.                    Re-engineering in the electronic environment will also need to include an objective examination of business processes in the courtroom.  Capabilities like electronic minutes, electronic orders, in-court updating, digital audio recording, and virtual witnesses via videoconferencing should compel a reconsideration of who does what and how during hearings.  For example, we know that in-court updates of documents and orders requires a practiced choreography between the judge and court staff to attain the same level of efficiency as traditional hearings, with the benefit of immediate generation of orders, elimination of duplicate back office data entry and processing that is now required following hearings.  The redesign of courtroom processes should be role based, without regard initially for who fills the roles.

The Committee spent considerable time discussing duties of courtroom staff in the electronic environment and members made various suggestions for redeploying staff in a manner that takes advantage of the new technologies, best supports the needs of the courtroom, and achieves the economies promised by digital technology.  For example, the Committee found that one of the most effective ways for the smallest courts to achieve “staffing to the most efficient norm” in the near-term is to efficiently divide the courtroom support duties between court administration and the judge unit staff.  In some counties in the 8th District this is already being done on many calendars.  Digital recording is used in the courtroom which frees the court reporter and /or law clerk to record the courtroom minutes and produce the court orders.  As part of Recommended Action 3, the designated new group should include within its scope the re-examination of courtroom business processes and roles.

Re-engineering court processes has the potential for the greatest transformation of court business beyond the individual changes effected by each individual option.  For example, if e-citation is used in combination with other electronic options such as auto assess (to assess and disperse payments), auto referral (to automatically refer over-due cases to a collection agency), and automated payment (through the web or phone), approximately 1.2 million of the 2 million cases filed with the courts each year would be processed with little or no human intervention.  Significant reductions in staff levels can then be made without a corresponding decline in service to the public.  The NCSC estimates from the Minnesota e-PDQ data (data collected annually on staff duties and responsibilities) that workflow re-engineering promises an additional 30% savings in staff FTEs over and above the economies that are achieved from the individual initiatives.  Confirming the potential significance of this transformation is a Utah study concluding that the bulk of clerical work in court administration can be automated.

Recommended Action 3 describes the need for a group of the Judicial Council to immediately begin constructing a long-term service delivery plan.  Such a plan should marry overall workload reengineering to the transformative options being considered.  Under the long-term service delivery plan, each new technology or initiative would be required to contribute to the long-term service delivery strategy.  Moreover the existence of an agreed upon strategy as to the direction in which the branch is headed will encourage near-term decisions and actions that align with and support movement toward that goal.

# Strategy:  Legislative and Court Policy Reform

In the course of reviewing options for consideration, the Committee examined the excellent report of the Non-Felony Enforcement Advisory Committee (NEAC, 1997). The recommendations made by that group were largely not acted upon after the report was issued.  This Committee unanimously felt that the NEAC recommendations needed to be seriously reconsidered as soon as is possible.  The Committee also directed staff to ascertain the extent to which the judicial branch is able to effectuate changes in policy and practice without action or involvement of the legislature or others outside of the judicial branch (see Appendix I).  It appears to the Committee that at least one major initiative, the expansion and creation of uniformity in the payables list, is both consistent with the NEAC recommendations and within the authority of the judicial branch to implement in the near-term.

The court will also need to help the legislative branch prioritize the work of the court and shift those disputes that are administrative in nature to an executive agency for resolution.  Adjudicatory priorities must be identified and alternative adjudicatory processes for non criminal cases must be considered. For example, the courts need to show their support for the Department of Vehicle Services (DVS) efforts to upgrade their technology, and will also need to help re-educate the legislature that oversight of administrative matters, such as proof of insurance, registration, and driver’s licenses, not only is best administered by DVS, but is also the most effective and efficient use of scarce tax resources.

Other portions of the NEAC report will require legislative action and consultation with the other branches of government.  The Committee believes that those recommendations should also be pursued vigorously.

# Strategy:  Structure/governance issues

Although some of the fundamental changes will continue to be driven by new technological opportunities, other forces in the larger environment are equally important in driving the courts toward new business strategies and processes.  One such strategy that began with state funding and continued with the creation of the Judicial Council, is for the court to redesign itself in the model of a single enterprise, rather than 89 or 10 separate organizations.   Policy, management structure, and service delivery designs that support the “single entity” model not only promote consistency throughout the state, but are also necessary to achieve the kind of large-scale cost savings needed in the future.

The Committee agreed that ten judicial districts are probably not needed and briefly reviewed proposed criteria for determining the optimal number of judicial districts.  The Committee also listened to ideas for multi-county administrative management units, based on judicial assignment areas.  The Committee strongly supports work underway in the 5th, 8th, and 9th Judicial Districts to move toward multi-county court administrators overseeing a judicial assignment area.  It is clear that if future service delivery is provided from both centralized locations as well as local facilities, then a new management structure will be required that supports both the new hybrid system of service deployment and also promotes the “single business entity” concept .

The Committee decided to recommend that a separate group be tasked to consider the need for structural changes as part of a larger redesign of the court overall.

# Recommended Options

The strategies outlined above served as guideposts, helping the Committee select options that were consistent with a vision of a high-functioning court of the future, one that is successful through innovation and deliberate planning, despite the twin challenges of impending work force declines and long-term funding reductions.  On a more prosaic level, the Committee generally selected options that would support staffing to the most efficient norm (increase staff productivity, particularly in the smallest courts), were relatively easy to implement, provided large cost savings, and would achieve savings in the short term.  (An option was considered “short term” if it was believed that savings from that option would occur within two years.)

The potential for cost savings was not necessarily the determining factor as to whether the Committee chose to recommend an option.  For example, centralizing probate annual reviews which include the hiring of specialized staff, such as auditors, was identified as a low savings option, but was regarded by the Committee as a good business practice, relatively easy to adopt.

The recommended options are shown summarized and categorized by long-term strategy in Table 1 below.  Also included in this table are promising options that the Committee referred for further study.

Table 1 – Recommended and Referred Options by Strategy

(Options highlighted in italics were referred for further study.  See Appendix D, p. 25.)

Strategy:  Staff to the most efficient norm

- Centralize payables processing

- Centralize/regionalize mandated services

- Centralize probate annual reports

- Expand use of subordinate judicial officers

Strategy: Work flow re-engineering in the electronic environment

- Implement traffic citation and criminal electronic filing

- Implement in-court updating

- Implement civil electronic filing

- Implement document scanning

- Upgrade the WAN to support e-documents statewide

- Re-engineer workflow and service delivery throughout the courts

Strategy: Legislative & court policy reform

- Increase payables

- Pursue NEAC initiatives

Strategy:  Structural/governance issues

- Redistricting

More detailed descriptions of the recommended options follow.

- Centralize payables processing.  This option consists of three sub-options.

- Process payments centrally.  Payments for payables are sent to a central location by mail, IVR (interactive voice response or phone payments), or IWR (interactive web response or web payments) and processed on one location.

- Implement Auto Assess.  MNCIS automatically splits the payments to the appropriate recipient.

- Implement automated referral to collections.  Cases are automatically and electronically referred to a collection agency when the payer date is exceeded or when a payment plan payment is missed.  No clerk action is involved in referring the case.  Collected payments are automatically receipted into MNCIS.

- Centralize/regionalize mandated services.  This option begins with jury services.  Centralize and out-source processing of jury summons.  Regionalize processing of juror qualification questionnaires.

- Centralize probate annual reports.  Centralize the processing of probate annual reports for conservatorships and guardianships including annual accounting and well-being reports.  Hire qualified staff to do the work.

- Increase payables.  This option consists of four sub-options.

- Establish a fine schedule for all petty misdemeanors that are payables to minimize or eliminate staff time in setting fine amounts.

- Expand the list of misdemeanors that are payables.

- Expand the list of ordinance violations that are payables.

- Eliminate multiple fines (Some statutes are payable only in part and need staff intervention in order to be properly assessed thereby interfering with any economies that could be gained through automated processing.  An example of this is 169A.35 sub. 2 or 3, an open bottle violation.  A citation issued to a passenger is payable, but a citation issued to the driver requires a mandatory appearance.)

- Expand use of subordinate judicial officers.  This option consists of four sub-options.

- Use hearing officers for all fine mitigation hearings (payable petty misdemeanors and non-traffic misdemeanors, traffic citations, parking citations).

- Centralize processing of fine mitigation services online and/or with regionally located hearing officers, using ITV where appropriate.

- Use pro tem attorneys for conciliation, housing and some mental health hearings.

- Regionalize referees, using ITV where appropriate.

- Implement traffic citation and criminal electronic filing.

- Receive traffic citations from law enforcement agencies in electronic form and process them into MNCIS as digital documents and/or data.

- Receive criminal complaints electronically and process them into MNCIS as digital documents and/or data.

- Support electronic charging and electronic signatures as required to implement electronic filing of adult criminal cases into MNCIS.

- Implement civil electronic filing.  Electronically file all case initiation filings and subsequent case filings for all civil case types into MNCIS.  Combined with electronic document storage and paper document scanning (where necessary), this option replaces the paper case file with the electronic case file.

- Implement document scanning.  All paper documents are scanned immediately after filing and attached to the MNCIS case record as an object.  This creates an electronic case file.

- Implement in-court updates.  This option consists initially of three sub-options.

- Make MNCIS minute entries in the courtroom.

- Produce an electronic sentence order that can be printed out in the courtroom.

- Produce additional electronic orders in the courtroom where appropriate.

- Upgrade the wide area network (WAN) to support electronic documents statewide.  The electronic case files are available at all court locations.  This extends the capability in the civil electronic filing option to access electronic case files regionally, allowing for remote case processing.  See Appendix J for a map of current WAN locations

# Recommended Priorities

The Committee prioritized its recommended options into three levels of decreasing importance as follows.

Priority 1

- Centralize payables processing

- Standardize collections processing and referral

- Expand and standardize payables and, as needed, change corresponding statutes

- Implement traffic citation and criminal electronic filing

- Implement in-court updates

Priority 2

- Centralize/regionalize mandated services

- Centralize probate annual reviews

Priority 3

- Expand use of subordinate judicial officers

- Implement civil electronic filing

- Implement document scanning

- Upgrade the wide area network to support electronic documents statewide

In general, the recommended options were prioritized according to how well they promoted the vision for the court’s future, increased staff productivity, were consistent with the court’s business priorities, and were perceived as relatively easy to implement.  The following Table 2 attempts to graphically depict the priority preferences of the Committee.

Priority level 1 options tend to be relatively easy to implement and promise to yield significant savings in the short term.  A notable exception to this concerns the “Expand Payables” option.  This option was viewed as being partially “easy” (increasing payables on the state payables list, which can be done immediately by court action) and partially “hard” (it contains components that would require statute change).  To indicate this split, the option is listed twice in Table 2.

Priority level 2 options involve the centralization of mandated services and probate annual reports.  Although both of these options are thought to result in relatively moderate cost savings, it is believed that centralization of these services will result in higher quality service delivery because of the staff specialization that will occur through centralization.

Priority level 3 options tend to be either lower in savings and/or longer to achieve savings than other options.  But mostly, although still recommended by the Committee, Priority level 3 options were just viewed as being less compelling than the Priority 1 and 2 options.

Finally, the Committee found that while individual projects may yield some cost savings, the largest potential cost savings would come when business processes were re-engineered to take advantage of the new technologies.  The Committee recognized that an effort to re-engineer the court’s work processes in total would be a long-term initiative with many obstacles.

Table 2

# Summary of Recommended Actions

- The Judicial Council should select four or five initial options to implement statewide.

- The Judicial Council should establish a group to formulate a high-level work plan (sequence, schedule, resources) to implement the selected options as soon as practicable.

- The Judicial Council should immediately establish a group to study the longer range options implied by the vision for future service delivery (redistricting, reengineering of back office and courtroom duties and processes, etc.)

- The Judicial Council should formulate a communication plan no later than August 2008 that directs a small team to visit every district to discuss the Judicial Council recommendations, the ASD Committee report, and the FY09 budget.

- The Judicial Council should review and approve any new appointments of district administrators if vacancies occur until an appropriate group (Recommendation 3 above) considers possible redistricting or consolidation proposals.

# Appendices

Appendix A – NCSC Scope of Work document

Appendix B – Partial Source List for Options

Appendix C – Other Potential Options; Other Options Studied

Appendix D – Best Practices

Appendix E – Cost Data; Cost Notes

Appendix F – Implementation Time Horizon

Appendix G – Stakeholders

Appendix H – Authorization

Appendix I – Electronic Infrastructure Map of Minnesota

Appendix J – Short Descriptions of each Option

Notes on Appendices

Appendices E,F, G, H, and J document the information gathered on the recommended options.  The information in the appendices should not be viewed as complete nor exhaustive, but rather reflective of an effort to collect readily available information in a relatively short time frame.  Moreover, assessments of cost and time to implement were often necessarily guesses, with fairly wide ranges in some cases. Lastly, it was also recognized that the manner and speed of implementation will also determine start-up costs.  Options accepted by the Judicial Council will therefore require more detailed analysis, especially as to how an option is to be implemented (e.g. statewide or county by county) to accurately determine reliable implementation costs and expected net savings.  Appendix E documents the cost information gathered, followed by cost notes that describe the assumptions used in costing the option.  It should be noted that the estimated costs found in Appendix E generally do not include implementation costs for new projects.  The “next step” to any option accepted by the Judicial Council should be a detailed implementation plan that includes implementation costs.

Appendix F shows the estimated time horizon to achieve cost savings of each option.  The most common current implementation status described for each option is either “none,” meaning there is not currently a specific roll out plan for implementation of the option, followed by “county by county.”  In a “county by county” implementation plan there is no overall time line for statewide implementation, rather the project is implemented as local jurisdictions become willing and/or able to participate in the project.  Implementation costs will increase if an option is viewed as requiring an accelerated time horizon to statewide implementation.

Appendix G describes the Committee members’ perceptions of stakeholder support for an option.  A low score (near one) indicates a perception that a stakeholder would support an option.  A high score (near three) indicates a perception that a stakeholder would NOT support an option.  In general, the more stakeholders viewed by the Committee as likely to oppose an initiative, the more likely the Committee viewed the option as difficult to achieve or “hard.”  But the Committee was also likely to view an option as “hard” to achieve if a key stakeholder with significant policy authority was perceived as being likely to oppose an option.  For example, if judges were likely to oppose an option within their authority to change or the legislature was likely to be opposed to an option that required a statute change, then the option tended to be classified as “hard” to achieve, regardless of the number of other stakeholders who might support it.

Appendix H indicates the policy authority needed for the option, such as a change in statute.  Most of the options considered were within the authority of the Judicial Council to enact.  Lastly, Appendix J provides a short written description of each recommended option.

## Appendix A
NCSC Consulting Services

Scope of Work

Minnesota Access and Service Delivery Redesign Project

General Approach

The following approach will be used to identify a new strategy for service delivery and a set of redesigned business processes to support a more efficient provision of court services to the public:

- Perform a quick high-level assessment of costs, service capabilities, service requirements and potential reengineering business process targets and strategies.

  - Describe high-level cost allocations.

  - Disaggregate high-level allocations by major business process.

- Document and prioritize current service capabilities.

  - Determine which capabilities are consistently in scope as court services statewide.

  - Describe high-level capabilities.

  - Disaggregate key capabilities.

  - Rank current capabilities.

- Document and prioritize desired service capabilities.

  - Identify criteria for ranking capabilities.

  - Define customer-desired service capabilities and service levels.

  - Adjust current capabilities list to add or delete as required.

  - Adjust current service levels to increase or decrease as required.

  - Rank desired capabilities.

- Prioritize business processes to deliver required service capabilities.

  - Identify criteria for ranking business processes to redesign.

  - Segregate target business processes by time and resources required to implement.

  - Rank target business processes.

- Develop a phased implementation plan for the new business processes.

  - Develop a process for deciding which options to implement first.

  - Select business processes for redesign.

  - Document business cases for successful implementation.

- Document repeatable process for maintaining service delivery strategy.

The approach distinguishes current business capabilities and processes from customer-desired capabilities.  It also distinguishes internal capabilities and processes that are hidden from customers and provide intermediate outputs from customer-facing capabilities that deliver business value to end users.  Finally, it distinguishes business capabilities that provide customer value from business processes that the court system uses to deliver the capabilities.  This distinction is important because a given capability can be delivered to customers in multiple ways using multiple business processes.  The capability is “what” is delivered.  The business process is “how” it is delivered.

Tasks and Deliverables

Task 1:  Perform an initial assessment of service improvement opportunities.  The NCSC project team will spend three days on-site making an initial assessment of the services delivery situation.  The team will document the current high-level business cost allocations.  The largest cost allocation categories will then be disaggregated into business processes (cost of judges trying cases, etc.) where possible.  On-going infrastructure costs will be included in the analysis and allocated to specific business processes as required.  Key cost assumptions will be documented (courthouse in every jurisdiction, etc.).

Interviewees will include internal court staff with knowledge of and expertise in the detailed budgets, business processes and project business cases.

Task 1 Deliverable:  A short and informal oral assessment report describing (1) the current cost allocation structure, (2) future service delivery requirements and (3) targets of opportunity for business process reengineering to reduce costs.

Task 2:  Document and prioritize current service capabilities.  If courts across the state vary in what array of services they provide, it can be a difficult exercise to make the initial determination of what is within scope for formal statewide service capabilities.  For example, some courts may offer restitution or mental health assessment services and others may not.  Once the courts define what high-level service categories will be provided statewide, it becomes progressively easier to tease out what the current service capabilities are.  As with the overall project, it is critical to describe all capabilities in terms that do not make implicit assumptions about delivery mechanisms or technology.

The NCSC project team will then work with the Minnesota project team to prioritize current service capabilities from an internal point of view.  The key step will be to facilitate the decision-making process of the Judicial Council Access and Service Delivery Committee.  The ranking of capabilities will be done using the best available data on associated costs.

Task 2 Deliverable:  A description of (1) prioritized current service capabilities and (2) their costs.

Task 3:  Document and prioritize desired service capabilities.  The identification of desired and/or required service capabilities should proceed along two paths.  With the help of the project teams, the Judicial Council Access and Service Delivery Committee will look at internal business processes that support customer services, apply a budget constraint based on expected funding levels to prioritized current capabilities, and determine what capabilities can be supported and delivered without any redesign.  The project teams will facilitate a small focus group of court customers to specify what desired capabilities should exist from the viewpoint of the public, litigants and funding agencies without reference to current funding constraints or delivery mechanisms.  These two approaches will then be reconciled as a single ranking of desired service capabilities.

Task 3 Deliverable:  A reconciled and prioritized set of desired and/or required service capabilities from both internal and customer points of view.

Task 4:  Identify business processes to deliver the required service capabilities.  This is the core of the project.  The selection of target business processes will depend on several criteria:  impact on cost structure, required resources to implement, implementation timing, impact on desired customer services, impact on desired customer service levels, and other factors.

Task 4 Deliverables:

- A process for prioritizing and choosing business process and service options

- A target set of business processes and resulting service capabilities to redesign

- A ranking of target business processes and resulting service capabilities based on a tradeoff analysis

- High-level cost estimates for target business processes and resulting service capabilities

- Typical timelines to realize savings from target service capabilities

- Presentation on Task 4 Findings to Judicial Council

Task 5:  Develop a phased implementation plan for the new business processes.  It will be important to both deliver solid and real business value (increased service levels with decreased costs) in the short-term and put in place the ability to incrementally improve the entire system in the long-term.  A balance between these two objectives will help the court show immediate progress while avoiding the creation of roadblocks to even more significant improvement.

Task 5 Deliverable:  A high-level implementation strategy for the prioritized target service capabilities and business processes.

Task 6:  Document a high-level process for maintaining the service redesign and delivery strategy.  This deliverable will enable Minnesota court staff to update the strategy in the future as needs and circumstances change.

Task 6 Deliverable:  A high-level process for updating service delivery strategy.

Project Team

The NCSC project team should consist initially of staff with the following skill sets:

- Extensive knowledge of court budgets and funding processes

- Extensive knowledge of court business process redesign methods

- Ability to facilitate identification and documentation of business requirements (capabilities and service levels)

- Ability to identify opportunities to better utilize technology

These staffing requirements can be met with a three-person team:

- Dan Hall, Vice President Court Consulting Services (budgets, funding)

- Tom Clarke, Vice President Research and Technology (business process redesign, technology support)

- Heidi Green, a consultant with the Minnesota courts (court business process and business requirements).

In later phases of the project, business processes experts can be used in short-term iterations to work on the details of new best practices for service delivery for specific capabilities.

Project Schedule

| Task | Schedule | Task End Date | On-Site Trip | Tele/Video Conference |
| --- | --- | --- | --- | --- |
| 1 | Weeks 1- 3 | February 29th | Feb 27 - 29 |  |
| 2 | Weeks 4 - 6 | March 21st |  |  |
| 3 | Weeks 7 - 10 | April 18th | Week of April 4th |  |
| 4 | Weeks 11 – 20 | July 30th | Week of July 13th | Week of May 19th |
| 5 | Week 2 |  |  |  |
| 6 | Week 1 |  |  |  |
| Project team will meet with the Judicial Council in July at a date to be determined to present and discuss the project findings. |  |  |  |  |

Note:  The schedule assumes a start date of February 11, 2008

Detailed tasks by week will be provided to the Minnesota project team lead (Heidi Green) during the first week of the project.

## Appendix B
Partial List of Sources for Potential Options

- Minnesota Judicial Workload Assessment Report, 2002

- Minnesota Court Staff Workload Assessment Report, 2004

- ePDQ data, 2006

- Minnesota District Court Transformation Project Report, 2003

- Working Group on Criminal Justice System Efficiency Report, 2003

- Non-Felony Enforcement Advisory Committee Report, 1997

- Budget Contingency Working Group Report, 2003

- Project Staff Meetings

  - AOC staff

  - District Administrators and staff

- Utah Comprehensive Clerical Committee Draft Report, 2008 (confidential)

- Solicited suggested from district court administrators

- Solicited suggested from key AOC staff

- Solicited suggested from ASD Committee members

- Unsolicited suggestions from court system staff (anonymous letter)

## Appendix C
Other Potential Options

- Mandate pre-court diversions statewide.

- Eliminate pre-sentence investigations for misdemeanors.

3.	Give probation officers authority to impose sanctions for violations subject to court review at the request of the violator.

- Consolidate judicial districts from ten to six or four.

- Eliminate some civil case types.

- Decriminalize various categories of misdemeanors or redefine non-violent misdemeanors as petty misdemeanors.

- Increase the list of offenses that may be resolved by the administrative payment of a fine without a court appearance.

- Handle a first failure to appear to provide proof of insurance with an administrative process.

- Handle juvenile petty offense as administrative payables.

- Make mandatory use of non-court ADR in all civil and family cases.

- Encourage increased use of private courts.

- Out-source pro se services.

- Out-source mediation services.

- Convert to virtual state law library.

- Standardize on best calendaring and case flow practices (combined omnibus, pre-trial and settlement hearings).

- Standardize on best jury management practices (one day one trial, etc.).

- Use one law clerk for every two judges.

- Pay executive branch agencies to operate ITV remote facilities.

- Increase use of remote telephone or video interpreting (use of in-person interpreters for trials only).

- Increase use of ITV for hearings, judges’ meetings, and other routine events.

- Handle conciliation court administratively (possibly with hearing officers).

- Eliminate civil jury trials.

- Transfer name change and civil administrative licensing hearings to executive branch.

- Eliminate misdemeanor orders in favor of court minutes.

- Move various driver privilege functions from courts to DPS and law enforcement.

- Use voluntary placement of juveniles without court involvement if not contested.

- Regionalize, centralize, and put online as much pro se materials and support as possible.

- Provide a centralized online database of standard rulings for use by law clerks and judges.

- Eliminate reporting and recording for juvenile and traffic matters.

- Eliminate the right to a jury trial for misdemeanors.

- Combine the Rule 5 and 8 appearance hearings in all criminal cases.

- Require binding arbitration, paid for by parties, for property disputes in marriage dissolution cases.

- Fund only two ADAs per district.

- Make in-court updating mandatory for all case types, especially orders in juvenile delinquency and child welfare/dependency cases.

- Standardize all policies, procedures, and practices statewide.

- Merge EOD and Court Services.

- Automate the referral of all delinquent accounts to the collection agency statewide (ACS to MNCIS passback).

- Eliminate the GAL program.

- Eliminate the Race Census Data program.

- Eliminate the Self-Help program.

- Reduce the number of Pro Se forms available.

- Use business volunteers to analyze and redesign court processes.

- Improve scheduling of court appearances to reduce continuances (defendants, defense attorneys, prosecutors, interpreters).

- Reduce the list of offenses required to have a bail study and allow the court discretion in ordering bail studies.

- Make pre-sentence investigations for felonies discretionary.

- Standardize CMS codes for case events and outcomes statewide.

- Train judges regularly on basic caseflow management best practices for criminal cases (omnibus date set at Rule 8 appearance, omnibus hearing 14 days after appearance, preliminary discovery to defense at first court appearance).

- Schedule an omnibus hearing only if the attorneys indicate the need for a contested hearing.

- Venue for all proceedings in a juvenile delinquency case will be with the residence county.

- Juvenile delinquency diversion should be a pre-filing program that involves no court appearances.

- Consolidate detention and arraignment hearings for juvenile delinquency cases.

## Appendix D
Best Practices

- Refer practice of staff intervention in payables to COPS.

- Refer proof of insurance process review to COAW.

## Appendix E
Option Cost Assessment by Priority

Appendix F
Option Time Horizon by Priority

## Appendix G
Stakeholders Assessment By Priority

Note:  This is the Committee’s assessment of probable stakeholder positions.

## Appendix H
Policy Authority by Priority

## Appendix I (MNET)

## Appendix J
Options Short Description By Priority

Centralization does not necessarily mean that such services will be located in St. Paul.  In an “e-everything” future, centralized services, where appropriate, may well be located in other parts of the state or outsourced.

The committee discussed the fact that the judge unit is budgeted at 100%.  Court administration has absorbed the majority of the budget shortfall and is operating at about 85% of need.  The intention of this strategy would be to better balance workload across employee groups.

The Non-felony Enforcement Advisory Committee ("NEAC") was established by the 1993 Legislature in response to concerns about the proportionality, prosecution, and enforcement of non-felony offenses.  The Committee's specific mandate, as amended in 1995, was to:

- analyze relative penalty levels for non-felony crimes against the person, low-level felony property crimes, and crimes for which there are both felony and non-felony penalties; and

- recommend any necessary changes in Minnesota law to achieve the following:

- proportionality of penalties for gross misdemeanors, misdemeanors, and petty misdemeanors;

- effective enforcement and prosecution of these offenses; and

- efficient use of criminal justice system resources.

The Committee consisted of a broad cross section of the criminal justice community, including legislators, city and county attorneys, judges, criminal defense attorneys, probation officers, law enforcement, law professors, and public members.  Appointments to the Committee were made by the chairs of the senate crime prevention and house judiciary committees.  The Committee was chaired by Sue Dosal, the State Court Administrator.

Options shown in italics were recommended for further study. Re-engineering workflow and service delivery will take a concerted effort to imagine and design the court of the future; to change workflow to take optimal advantage of the new technologies while promoting the court’s strategic priorities.  Similarly, additional study is needed to consider the structural and governance issues required to support the court of the future.  Redistricting needs to be considered along with re-engineered workflow.  See Recommended Action 3.  The Committee recognizes that staffing to the most efficient norm will require that we continue to study issues of hours of counter operations, etc., in the near-term, but until a long-term strategy is developed, these items should at this time be left to the districts for determination.  Similarly, while successfully pursuing NEAC initiatives is a long-term initiative, some work may begin immediately.  Therefore, the Committee recommends that the legislative strategy options be referred to the COPS committee for development of a legislative strategy and immediate work on the state payables list.